# Analysis of the Implementation of Teaching Factory Development by Using the Critical Path Method

# Trisna Mesra 1, Melliana2, Fitra3, Azmi4 and  Dini Febriyanti Agustin5

12345 Sekolah Tinggi Teknologi Dumai, Jl. Utama Karya Bukit Batrem II, Kota Dumai, 28815, Indonesia

| Article Information |  | ABSTRACT |
| --- | --- | --- |
| Received: Revised: Available online: |  | A project is a unique series of interrelated activities to achieve a certain result and carried out within a certain period of time. However, most projects are implemented not using proper and appropriate management, so that it has an impact on wasting time and project budget costs which causes low profits for contractor companies.Based on these problems, the authors conducted research using the CPM (Critical Path Method) method in order to find the optimal time in project implementation and to obtain optimal budget costs in implementing the Teaching Factory development project at SMKS Taruna Persada Dumai. In addition, this study also uses CV (Cost Variance) and SV (Schedule Variance) to determine the performance index and project performance. Based on calculations through the CPM (Critical Path Method) method, the optimal time for the implementation of this project is 65 working days, with the optimal cost based on the CPM (Critical Path Method) calculation obtained a cost of Rp. 188,044,781. Based on the calculation of performance through the CV (Cost Variance) and SV (Schedule Variance) methods, the Teaching Factory project obtained a CV value of -Rp. 4,949,624 and the SV value of Rp. 7.398.376. This states that the Teaching Factory development project in terms of work implementation is faster than planned with the costs spent being greater than budgeted. |
| Keywords |  |  |
| Project Management, CPM, NPV, CV, SV |  |  |
| Correspondence |  |  |
| Phone: +62 813 7871 3803 E-mail: trisnamesra74@gmail.com |  |  |

# INTRODUCTION

Project activities can be interpreted as a temporary activity that lasts for a limited period of time, with the allocation of certain resources and is intended to produce products or deliverables whose quality criteria have been clearly outlined (Soeharto, 1999). Project activities in the process of achieving their final results are limited by time and cost. The implementation of projects within the organization is generally carried out to achieve specific objectives, the activities are clearly defined when it starts and when it ends, and there are restrictions on funds to carry out these project activities. In addition to the accuracy of time estimates, confirmation of the relationship between the activities of a project is also needed for planning a project.

SMKS Taruna Persada is one of the implementing elements of the teaching factory project development. This teaching factory development project was carried out for the learning needs of entrepreneurship for SMKS Taruna Persada Dumai students. In working on the project, workers have not used the CPM method in determining the time and costs required. So far, workers in determining time and costs are only based on experience. SMKS Taruna Persada Dumai often have problems in the completion time of development projects because the completion time does not match the time agreed with the previous workers. This will have a negative impact because the school will incur more costs with the inaccurate time of project completion.

According to Levin and Kirkpatrick (1972), the Critical Path Method (CPM), which is a method for planning and monitoring projects, is the most widely used system among all other systems that use the principle of network formation. With CPM, the amount of time required to complete the various stages of a project is considered to be known with certainty, as is the relationship between the resources used and the time required to complete the project. CPM is a project management model that prioritizes cost as the object being analyzed (Siswanto, 2007). CPM is a network analysis that seeks to optimize the total project cost by reducing or accelerating the total completion time of the project in question.

The objectives and benefits of the Critical Path Method (CPM) are as follows:

- To map out all the steps required to complete the project and identify a schedule for each priority and sequence involved.

- Shows the relationship of each activity to the whole project.

- Identify the relationship that should take precedence between activities.

- Show realistic cost and time estimates for each activity.

- Assist in the use of manpower, money and other resources by observing critical issues in the project.

The project scheduling that has been discussed previously does not include the company's stock of resources. Consideration of the available resources can change the life of the project because limited resources for an activity or activity can make the time to work on the activity or activity can make the execution time of the activity longer, and vice versa. we will use the critical path method Critical Path Method (CPM), reduction of project life and resource planning in the next sub-chapter (Santosa, 2009).

The first crisis trajectory method was used on construction projects at the Du Pont company in 1957. This method put more emphasis on project costs. This is different from PERT which places more emphasis on time uncertainty, and for research and development (R&D) projects. In CPM there is no application of statistical methods to accommodate the uncertainty. The CPM also discusses the existence of a bargain or trade-off between the time schedule and project costs (Santosa, 2009).

CPM assumes that the project life can be shortened by adding labor, equipment, and capital resources for certain activities. If there are no other provisions, then the time for carrying out the activity is considered to be in "Normal" conditions, the execution time under normal conditions is called normal time (Tn). The cost of carrying out an activity under normal conditions is called the normal cost (Cn). Additional manpower or overtime work can reduce normal time. The addition of the workforce means additional costs. The normal time Tn is usually the longest time for an activity while the normal cost Cn is the cheapest cost. If all the resources owned by the company are mobilized so that an activity can be completed as quickly as possible, then the activity is said to be Crashed. The crashed condition is not only related to the fastest time, but also to the biggest cost. In the crashed condition, the time for carrying out the activities is the Cc fee.

# METHOD

The research was conducted at the Taruna Persada Dumai Vocational School, which is located on Jalan Abdul Rab khan KM 05, Bukit Timah Village, Dumai Selatan District, Dumai City, Riau. This research was conducted on the teaching factory building construction project. This research will take place in March 2021.

The types of data used in this study are secondary data and primary data. Secondary data are books, journals and data obtained directly from SMKS Taruna Persada Dumai related to the discussion. Then, primary data is data obtained by researchers directly from the first party related to time data in project implementation, costs incurred in project implementation, as well as tools and materials used in project implementation.

In the implementation of data collection can be done in several ways or tools used to obtain research data called the term data collection techniques, namely observation, interviews, and documentation. The stages of data analysis used in this study are as follows:

- Descriptive statistics, namely analyzing data by describing the data that has been collected.

- Data processing using the CPM (Critical Path Method) method, with the following steps:

- Assess and identify project scope

- Describe, break it down into activities or groups of activities that are components of the project.

- Rearrange the components in point 1, into a chain in the appropriate order of dependency logic, providing an estimate of the timeframe for each activity that results from the description of the project scope.

- Identify the critical path (critical path) and float on the network.

- Draw conclusions from the results of research and processing with the methods used.

# RESULTS AND DISCUSSION

The data taken to conduct research on the Teaching Factory construction project for SMK Taruna Persada Dumai which was carried out in March, namely schedule data, description of project implementation activities, work time, pessimistic time, most likely time, optimistic time and budget plan. Data obtained from SMK Taruna Persada Dumai.

Calculation of project implementation time using the CPM method. Data description of activities as well as the time of each activity of the project implementation is required. Data description of project activities for the construction of teaching factory SMKS Taruna Persada Dumai can be seen in Table 1.

Table 1. Data Description of Teaching Factory Project Implementation Activities

| No | Description of activities |
| --- | --- |
| I | Preliminary Work |
| 1 | Preparation of tools and materials |
| 2 | Location Cleaning |
| 3 | Install bouwplank/measurement |
| A | Bangunan Teaching Factory |
| II | Teaching Factory Building |
| 1 | Foundation work |
| 2 | Foundation excavation work |
| 3 | Mobile Trench Excavation Works |
| 4 | Foundation sand fill work |
| 5 | P1 Reinforced Concrete Foundation Works |
| 6 | Rib work 1 brick |
| III | Bata Foundation Raben Jobs |
| 1 | Concrete And Structure Works |
| 2 | Column Work K1 Reinforced Concrete 20/20 cm |
| 3 | RB1 Concrete Beam Ring Work 15 x 20 Cm |
| IV | Wall work |
| No | Description of activities |
| 1 | Brick Wall Installation 1: 2 |
| 2 | Wall Plaster Installation 1: 2 |
| V | Door And Glass Works |
| 1 | Iron Panel Door Installation Work |
| 3 | The Job of Installing Door Frames and Rear Door Leaves |
| 2 | Installation of window frames and shutters |
| VI | Floor job |
| 1 | Soil embankment work under the ground floor Thickness 30 cm |
| 2 | 8 cm thick floor slab casting work |
| 3 | 40 x 40 . Floor Ceramic Installation Work |
| 4 | Acian job |
| VII | Ceiling Works |
| 1 | Plywood Ceiling + Frame Work |
| 2 | Ceiling List Job |
| VIII | Roof Frame Work |
| 1 | Light Steel Easel Installation |
| IX | Roof Covering Works |
| 1 | Metal tile roof installation work |
| X | Electrical Installation Work |
| 1 | Light installation work |
| 2 | Power outlet installation work |
| 3 | MCB box work |
| XI | Air compression installation |
| 1 | Air compression installation |
| XII | Painting Job |
| 1 | wall paint job |
| 2 | ceiling paint job |
| B | Doorsmeer Building |
| XIII | Foundation work and sanitation |
| 1 | Doormeer building foundation excavation work |
| 2 | Sanitation work |
| XIV | Pole and roof steel work |
| 1 | Pole construction installation |
| 2 | Installation of roof construction |
| XV | Floor job |
| 1 | Floor casting 13.4 x 20 M |
| 2 | Acian job |
| 3 | Installation of hydraulic equipment (single post H type hydraulic carwash) |
| XVI | Water machine installation work |
| 1 | Installation of water machine installation |
| No | Description of activities |
| XVII | Final Work |
| 1 | Finishing work |
| 2 | Final Cleaning |

Table 1 is a data description of the project implementation activities for the construction of the teaching factory at SMKS Taruna Persada Dumai. Detailed data on development activities and planned implementation times using the CPM method can be seen in Table 4.2.

Table 1. Detailed Data on Activities and Implementation Time

planned  with the CPM method

| Code | Type of activity | Work days | Worker | The number of workers | Preliminary Activities |
| --- | --- | --- | --- | --- | --- |
| A | Location cleaning | 3 | Craftsman | 1 | - |
|  |  |  | Helper | 2 |  |
| B | Preparation of tools and materials | 3 | Helper | 2 | A |
| C | Install bouwplank /measurement | 4 | Craftsman | 1 | B |
|  |  |  | Helper | 1 |  |
| D | Teaching factory building foundation excavation work | 3 | Craftsman | 1 | C |
|  |  |  | Helper | 1 |  |
| E | Mobile trench excavation work | 2 | Helper | 1 | C |
| F | P1 teaching factory reinforced concrete foundation work | 5 | Craftsman | 1 | C |
|  |  |  | Helper | 1 |  |
| G | Rib work 1 brick | 4 | Craftsman | 1 | D,E,F |
|  |  |  | Helper | 1 |  |
| H | Bata Foundation Raben Jobs | 4 | Helper | 2 | G |
| Code | Type of activity | Work days | Worker | The number of workers | Preliminary Activities |
| I | Teaching factory foundation sandfill work Concrete sloof work 20 x 20 Cm | 4 | Helper | 1 | H |
| J | Reinforced concrete K1 column work 20/20 cm | 5 | Craftsman | 1 | I |
|  |  |  | Helper | 1 |  |
| K | Reinforced concrete K1 column work 20/20 cm | 4 | Craftsman | 1 | J |
|  |  |  | Helper | 1 |  |
| L | Concrete ring work RB1 15 x 20 Cm | 5 | Craftsman | 1 | K |
|  |  |  | Helper | 2 |  |
| M | 1:2 . brick wall installation | 4 | Craftsman | 1 | L |
|  |  |  | Helper | 1 |  |
| N | Installation of wall plaster 1: 2 | 3 | Craftsman | 1 | M |
|  |  |  | Helper | 1 |  |
| O | The job of installing the frame + iron panel door leaf and frame + back door leaf | 3 | Craftsman | 1 | M |
| P | The work of installing windows + shutters | 2 | Craftsman | 1 | M |
| Code | Type of activity | Work days | Worker | The number of workers | Preliminary Activities |
| U | Light Steel Easel Installation | 4 | Craftsman | 1 | M |
| V | Metal tile roof installation work | 3 | Craftsman | 1 | N,O,P,U |
|  |  |  | Helper | 1 |  |
| W | Plywood Ceiling + Frame Work | 4 | Craftsman | 1 | M |
|  |  |  | Helper | 2 |  |
| X | Ceiling List Job | 3 | Craftsman | 1 | W |
|  |  |  | Helper | 1 |  |
| Q | Soil embankment work under the ground floor Thickness 30 cm | 3 | Helper | 1 | I |
| R | 8 cm thick floor slab casting work | 4 | Craftsman | 1 | Q |
|  |  |  | Helper | 1 |  |
| S | 40 x 40 . Floor Ceramic Installation Work | 5 | Craftsman | 1 | R |
|  |  |  | Helper | 2 |  |
| T | Finishing work | 2 | Helper | 1 | S |
| Y | Install the LED light | 1 | Craftsman | 1 | M |
| Z | Install the socket | 2 | Craftsman | 1 | Y |
| AA | MCB box work | 2 | Craftsman | 1 | Z |
| AB | Doormeer building foundation excavation work | 3 | Craftsman | 1 | C |
|  |  |  | Helper | 1 |  |
| AC | Sanitation work | 3 | Craftsman | 1 | AB |
| Code | Type of activity | Work days | Worker | The number of workers | Preliminary Activities |
| AD | Pole construction work | 5 | Craftsman | 1 | AB |
|  |  |  | Helper | 2 |  |
| AE | Roof construction work | 4 | Craftsman | 1 | AB |
|  |  |  | Helper | 2 |  |
| AF | Floor casting | 4 | Craftsman | 1 | AC,AD,AE |
|  |  |  | Helper | 1 |  |
| AG | Finishing work | 2 | Helper | 1 | AF |
| AH | Wall Paint Job | 4 | Craftsman | 1 | T,AG |
|  |  |  | Helper | 1 |  |
| AI | Ceiling Paint Job | 3 | Craftsman | 1 | X |
|  |  |  | Helper | 1 |  |
| AJ | Install electricity | 3 | Craftsman | 1 | AA |
| AK | Installation of air installation equipment | 4 | Craftsman | 1 | AH |
| AL | Installation of hydraulic equipment (single post H type hydraulic carwash) | 5 | Craftsman | 1 | AK |
| AM | Installation of water machine installation | 4 | Craftsman | 1 | AL |
| AN | Final work (finishing) | 4 | Helper | 1 | V,AI,AJ,AM |
| AO | Cleaning | 3 | Helper | 2 | AN |

## The project for the construction of the SMKS Taruna Persada Dumai teaching factory has a project price of Rp. 201,332,781,-. The price of the project includes planning a detailed price quote consisting of materials, wages, and tools used.

The desired time for the construction project of the SMKS Taruna Persada Dumai teaching factory is 90 days, to find out the time the work carried out meets the desired target can be calculated using the CPM method. The steps for processing time data using the CPM method are compiling a network diagram based on the time duration of each type of activity, calculating the earliest starting time (ES), calculating the latest starting time (LS), calculating the earliest finish time (EF), calculate the most recent finish time (LF), and slack. The activity trajectory that has a slack value of 0, then the activity is in a critical path. The steps of data processing using the CPM method are as follows.

1. Draw up network diagrams

Prepare a network diagram of the Teaching Factory project activities using the AOA (activity on arrow) approach based on the planned data including the duration of the working day of each type of activity in Table 4.2. CPM network diagrams can be

seen in Figure 1.

Figure 1. Network Diagram of Teaching Factory Development Project for SMK Taruna Persada Dumai

Figure 1 is a network diagram of the teaching factory project activities for the Taruna Persada Dumai Vocational High School in Dumai.

2. Determine the critical path and project completion time

The next step is to calculate the ES, EF, LS, LF, and slack from each activity time to determine the critical path. Critical trajectory on the project to determine and know the project completion time. The calculation results can be seen in Table 2.

Table 2. Calculation of ES, EF, LS, LF and Slack with the CPM . Method

| Code | Processing time | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| A | 3 | 0 | 3 | 0 | 3 | 0 |
| B | 3 | 3 | 6 | 3 | 6 | 0 |
| C | 4 | 6 | 10 | 6 | 10 | 0 |
| D | 3 | 10 | 13 | 12 | 15 | 2 |
| E | 2 | 10 | 12 | 13 | 15 | 3 |
| F | 5 | 10 | 15 | 10 | 15 | 0 |
| G | 4 | 15 | 19 | 15 | 19 | 0 |
| H | 4 | 19 | 23 | 19 | 23 | 0 |
| I | 4 | 23 | 27 | 23 | 27 | 0 |
| J | 5 | 27 | 32 | 30 | 35 | 3 |
| K | 4 | 32 | 36 | 35 | 39 | 3 |
| L | 5 | 36 | 41 | 39 | 44 | 3 |
| M | 4 | 41 | 45 | 44 | 48 | 3 |
| N | 3 | 45 | 48 | 52 | 55 | 7 |
| O | 3 | 45 | 48 | 52 | 55 | 7 |
| U | 4 | 45 | 49 | 51 | 55 | 6 |
| V | 3 | 49 | 52 | 55 | 58 | 6 |
| W | 4 | 45 | 49 | 48 | 52 | 3 |
| X | 3 | 49 | 52 | 52 | 55 | 3 |
| Q | 3 | 27 | 30 | 27 | 30 | 0 |
| R | 4 | 30 | 34 | 30 | 34 | 0 |
| S | 5 | 34 | 39 | 34 | 39 | 0 |
| T | 2 | 39 | 41 | 39 | 41 | 0 |
| Y | 2 | 45 | 47 | 49 | 51 | 4 |
| Z | 2 | 46 | 48 | 51 | 53 | 5 |
| AA | 2 | 48 | 50 | 53 | 55 | 5 |
| AB | 3 | 10 | 13 | 27 | 30 | 17 |
| AC | 3 | 13 | 16 | 32 | 35 | 19 |
| AD | 5 | 13 | 18 | 30 | 35 | 17 |
| AE | 4 | 13 | 17 | 31 | 35 | 18 |
| AF | 4 | 18 | 22 | 35 | 39 | 17 |
| AG | 2 | 22 | 24 | 39 | 41 | 17 |
| AH | 4 | 41 | 45 | 41 | 45 | 0 |
| AI | 3 | 52 | 55 | 55 | 58 | 3 |
| AJ | 3 | 50 | 53 | 55 | 58 | 5 |
| AK | 4 | 45 | 49 | 45 | 49 | 0 |
| AL | 5 | 49 | 54 | 49 | 54 | 0 |
| AM | 4 | 54 | 58 | 54 | 58 | 0 |
| AN | 4 | 58 | 62 | 58 | 62 | 0 |
| AO | 3 | 62 | 65 | 62 | 65 | 0 |

Table 2 is a calculation table using the CPM method to find the critical path and project completion time. Based on the slack value 0 indicates that the activity is an activity that is on a critical trajectory. The critical paths in the calculation table are: A, B, C, F, G, H, I, Q, R, S, T, AH, AK, AL, AM, AN and AO with a completion time of 65 days. After getting the critical path and project completion time, the next step is to create a critical path on the network diagram.

The calculation of wages is based on the cost of labor for each activity and then the total cost of wages for these activities. The wages that have been obtained from each activity are then multiplied by the working days of each activity. The cost of materials and tools does not depend on the calculation of the day, but based on each activity. The project cost budget for 65 days based on Table 4.7 is Rp. 188.044,781.

Figure 2. CPM Method Network Diagram

The desired completion time for the Teaching Factory project is 90 days. The teaching factory development project has a project price of Rp. 239,247,099. The project cost budget plan is based on the total details of the project price offer for 90 days of Rp. 201,332,781. The results of the project completion time using the CPM method were obtained for 65 days. Researchers do the calculation of materials, labor costs and wages, tools from the working day of each activity. The results of the project budget calculation for 65 days can be seen in Table 3.

Table 3. Results of the Calculation of the Project Cost Budget

| Code | Material | Cost (Rp) | Tool |
| --- | --- | --- | --- |
| A | - | Rp 900.000,00 | - |
| B | - | Rp 540.000,00 | Rp 6.500.000,00 |
| C | - | Rp 840.000,00 | - |
| D | - | Rp 630.000,00 | - |
| E | - | Rp 180.000,00 | - |
| F | Rp 7.150.268 | Rp 1.050.000,00 | - |
| G | Rp 2.842.560 | Rp 840.000,00 | - |
| H | Rp 6.772.192 | Rp 720.000,00 | - |
| I | Rp 2.885.000 | Rp 360.000,00 | - |
| J | Rp 8.579.000 | Rp 1.050.000,00 | - |
| K | Rp 7.640.000 | Rp 840.000,00 | - |
| L | Rp 4.670.000 | Rp 1.500.000,00 | - |
| M | Rp 5.100.000 | Rp 840.000,00 | - |
| N | Rp 2.520.000 | Rp 630.000,00 | - |
| Code | Material | Cost (Rp) | Tool |
| O | Rp 6.661.591 | Rp 360.000,00 | - |
| P | Rp 1.500.000 | Rp 240.000,00 |  |
| Q | Rp 4.920.000,00 | Rp 270.000,00 | - |
| S | Rp 6.618.700,00 | Rp 1.500.000,00 | - |
| T | Rp 550.000,00 | Rp 180.000,00 | - |
| U | Rp 9.440.000,00 | Rp 480.000,00 | Rp 304.850,00 |
| V | Rp 13.029.120,00 | Rp 630.000,00 | - |
| W | Rp 5.610.000,00 | Rp 1200.000,00 | - |
| X | Rp 902.000,00 | Rp 630.000,00 | - |
| Y | Rp 320.000,00 | Rp 120.000,00 | - |
| Z | Rp 210.000,00 | Rp 240.000,00 |  |
| AA | Rp 350.000,00 | Rp 240.000,00 | - |
| AB | - | Rp 630.000,00 | - |
| AC | Rp 1.447.000,00 | Rp 360.000,00 | - |
| AD | Rp 6.798.000,00 | Rp 1.500.000,00 | - |
| Code | Material | Cost (Rp) | Tool |
| AE | Rp 17.008.000,00 | Rp 1.200.000,00 | - |
| AF | Rp 2.051.000,00 | Rp 840.000,00 | Rp 1.237.500,00 |
| AH | Rp 4.250.000,00 | Rp 840.000,00 | - |
| AI | Rp 2.000.000,00 | Rp 630.000,00 | - |
| AJ | - | Rp 360.000,00 | - |
| AK | Rp 1.500.000,00 | Rp 480.000,00 | - |
| AL | Rp 9.500.000,00 | Rp 600.000,00 | - |
| AM | Rp 2.200.000,00 | Rp 480.000,00 | - |
| AN | - | Rp 360.000,00 | - |
| AO | - | Rp 540.000,00 |  |
| Total | Rp 188.044.781 |  |  |

Table 3  shows the results of the calculation of the project budget for 65 days of Rp. 188.044,781. Based on the details of the project price offer for 90 days, which is Rp. 201,332,781 there is a price difference of Rp. 13,288,000.

The S curve of the Teaching Factory project based on the CPM method shows that the project can be completed in 65 days. From the curve it can be seen to what extent the work process takes place. It can also be seen how many percent of the costs have been spent in the progress of work

Determining the performance index can be done through evaluating the project's performance at a certain point in time. There are various variables that can be used, the variables are BCWS (Budgeted Cost Of Work Scheduled), ACWP (Actual Cost Of Work Performed) and BCWP (Budgeted Cost Of Work Performed). From the three BCWS, BCWP and ACWP quantities, other quantities can be obtained, namely CV (Cost Variance) and SV (Schedule Variance). If the CV value is negative, it means that the project's performance in terms of costs is not good because the actual costs are greater than planned. If the SV is positive, it means that the execution of the work is faster than what was done and vice versa if it is negative, it means that there has been a lag behind what was planned. The project for the construction of the Teaching Factory SMKS Taruna Persada Dumai building has a project price of Rp. 239,247,099. Implementation of the desired project for 90 days which means for 3 months. Currently, the construction project for the Teaching Factory building has been running for 52 days. The CV and SV calculation data for the Teaching Factory building project at SMKS Taruna Persada Dumai can be seen in Table 4.

Table 4. Calculation of CV and SV Data for Teaching Factory Project

| No | Information | Cost |
| --- | --- | --- |
| 1 | Budgeted costs | Rp. 239.247.099 |
| 2 | BCWP (52 hari) | Rp. 138.231.657 |
| 3 | ACWP (52 hari) | Rp. 143.181.281 |
| 4 | BCWS (52 hari) | Rp. 130.833.281 |

Table 4 shows CV and SV calculation data consisting of ACWP, BCWP and BCWS values for 52 days. The results of the calculation of CV and SV can be seen as follows.

CV	= BCWP-ACWP

= Rp. 138.231.657 - Rp. 143.181.281

= -Rp.4.949.624

SV	= BCWP-BCWS

= Rp. 138.231.657 – Rp. 130.833.281

= Rp. 7.398.376

The calculation above shows that the results of the CV calculation are negative, namely -Rp.4.949,624 and the SV calculation is positive, which is Rp. 7,398,376. Based on the table of cost variance prices and schedule variants and their meaning means that in terms of carrying out the work faster than planned with costs spent greater than budgeted.

analysis

The desired time for the construction project for the Teaching Factory SMKS Taruna Persada Dumai building is 90 days, to find out the time for the work done to meet the desired target can be calculated using the CPM method. Calculation of time using CPM (Santosa, 2009) using data 1 planned time. The results of the project completion time using the CPM method obtained a time of 65 days based on the critical path with a total float and free float value of 0 in Table 4.6 and the network diagram in Figure 4.3.

The calculation of wages is based on the cost of labor for each activity and then the total cost of wages for these activities. The wages that have been obtained from each activity are then multiplied by the working days of each activity. The cost of materials and tools does not depend on the calculation of the day, but based on each activity. The project cost budget for 65 days based on Table 4.7 is Rp. 188.044,781.

Assessment of the performance index of the implementation of the Teaching Factory building for SMKS Taruna Persada Dumai can be calculated through CV and SV. Implementation of the desired Teaching Factory project for 90 days which means for 3 months. Currently, the construction project for the Teaching Factory building has been running for 52 days. shows that the results of the CV calculation are negative, namely -Rp.4.949.624 and the SV calculation is positive, which is Rp.7.398.376. Based on the table of cost variance prices and schedule variants and their meaning means that in terms of carrying out the work faster than planned with costs spent greater than budgeted.

# CONCLUSIONS

# The conclusions in this study are as follows, the optimal time in the implementation of the Teaching Factory construction project at SMKS Taruna Persada Dumai after being calculated using the CPM method is 65 days. While the optimal cost in implementing the Teaching Factory development project at SMKS Taruna Persada Dumai for 65 days after using the CPM method is Rp. 188.044,781 of the initial cost for 90 days of Rp. 201,332,781. There is a difference in cost reduction of Rp.13,288,000. The Teaching Factory construction project at SMKS Taruna Persada Dumai has a negative CV value of -Rp.4,949,624 and a positive SV value of Rp.7,398,376. This means that in terms of the execution of the work faster than planned with the costs spent being greater than budgeted.

# ACKNOWLEDGMENT

"Writer Dini Febriyanti Agustin would like to thank the parties who have assisted in the completion of the final project so that this journal was created".

REFERENCES

Handoyo dan Setiawan, R., 2021, Perencanaan Proyek Dalam Meningkatkan Efisiensi dan Efektifitas Jalan Tol Tebangi Besar-Kayu Agung Lampung PT Waskita Karya, Jurnal Manajemen Industri dan Teknologi Vol. 02, No. 01, Tahun 2021, Hal 132-143.

Husen, A. (2011). Manajemen proyek (edisi kedua).

Yogyakarta:Andi.

Khoiroh, S.M., 2018, Mengoptimalkan Crashing Project Pemasangan Saluran Rumah Di Perumahan X Dengan Pendekatan CPM-PERT, Jurnal Teknik Industri Heuristic vol. 15 no. 1, April 2018, hal. 39-48.

Lokajaya, I.N., 2018, Analisis Pengendalian Waktu Dan Biaya Pada Proyek Peningkatan Jalan dengan Metode CPM dan PERT, Jurnal Teknik Industri ISSN 1693-8232.

Santosa, B. (2013). Manajemen proyek : konsep & implementasi. Yogyakarta: Graha Ilmu.

Soeharto, I. (1999). Manajemen proyek dari konseptual sampai operasional (Edisi2). Jakarta:Erlangga.

Widyatmoko, Yurry. 2008. Analisis percepatan waktu menggunakan metode crashing pada kegiatan pemancangan di proyek Dermaga 115 Tanjung Priok dengan aplikasi program PERTMaster. Skripsi : Universitas Indonesia.

Suntana, N. dan Nalhadi, A., 2017, Analisa Infrastruktur Desa Sukaci-Baros dengan Metode Critical Path Method (CPM), Jurnal Sistem dan Manajemen Industri Vol 1 No 1 Juli 2017, 35-42 p-ISSN 2580-2887, e-ISSN 2580-2895.

Sutopo, W., Larasati, D.A.,  2020, Analisis Efektivitas Jadwal Proyek Implementasi Software dengan Critical Path Method, Jurnal INTECH Teknik Industri Universitas Serang Raya Vol 6 No 1 Juni 2020, 55-64 p-ISSN 2407-781X, e-ISSN 2655-2655.

Usman, R., Setiawan, B., 2020, Optimalisasi Penjadwalan Proyek Dengan Menggunakan Metode CPM Di Proyek LRT PULOMAS, Jurnal Terapan Teknik Industri Volume 1, Nomor 2, November 2020, 77-87 ISSN [print] 2722 3469 | ISSN [Online] 2722 4740.

Wastiono, T., Anggraini, R., Yuliarty, P., 2020, Penjadwalan

Proyek Mesin Auto Assembly Membrane Regulator Valve Di PT Omg Metode Critical Path Method (CPM), Jurnal Teknik Industri E-ISSN: 2615 – 3866.

NOMENCLATURE

ES 	meaning of Earliest Start

EF 	meaning of Earliest Finish

LF	meaning of Latest Finish

LS	meaning of Latest Start